## Slide 1
CAPITAL MARKET PROJECT MANAGEMENT TEAM (CMPMT)
The Nigerian Capital Market Master Plan (2015 – 2025)
Thursday 24th November, 2016
Implementation Update

## Slide 2: OUTLINE
Master Plan Implementation: Journey so far…
Update on CAMMIC Activities
Dashboard of Issues from Engagement with HMF, FIRS and DMO
Next Steps
CAPITAL MARKET PROJECT MANAGEMENT TEAM (CMPMT)

## Slide 3
E-Dividend
Direct Cash Settlement
Dematerialization
Robust public enlightenment
Transaction Cost Analysis
Promoting Non-interest Products
Recapitalization
Corporate Governance Scorecard
National Investor Protection Fund
CAMMIC Inauguration
Demutualization Framework
Responsive Rulemaking
Promoting ownership at National level
National Savings Strategy
Review of Major Laws
Strengthening Capacity
CAMMIC advocacy
National Literacy Week
Promoting New Listings
Market-wide Technology Infrastructure
Supporting Commodities
Nigerian Journal of Securities Market
Streamlined Bond Issuance Processes
National Financial Guarantor
Derivatives
Tax Incentives
Increase PFA asset allocation
Activate securities lending
Build commodities ecosystem
Dual Licensing Model
Liquidity measures
Jan 2015
Jul 2015
Jan 2016
Jul 2016
Jan 2017
Master Plan Implementation: The Journey So Far to 2025

## Slide 4
Update on CAMMIC Activities
Advocacy visits to top government officials (June 2016)
First roundtable with HMF (August 2016)
Second roundtable with HMF (October 2016)

## Slide 5
DASHBOARD OF ISSUES RELATED TO D.M.O.
DMO
SN | Task/Issue | Responsibility | Status | Completion level | Expected Outcome
1. | Release circular on coordination of supranational bonds | CAMMIC, HMF |  |  | Circular from HMF clarifying and streamlining supranational bond issuance process
2. | Diaspora bond issuance | DMO |  |  | Diaspora bond issuance in 2017
3. | Extending the yield curve | DMO |  |  | Longer benchmark yield curve to enable other categories of issuers raise longer term funds
4. | Sovereign sukuk issuance | DMO |  |  | First sovereign sukuk to be issued in 2017 to fund specific infrastructure projects
5. | Draft framework for FGN guarantees | CAMMIC, DMO, HMF |  |  | Framework outlining the requirements for obtaining sovereign guarantees
6. | Credit enhancement vehicle | CAMMIC, HMF |  |  | Launching of a national credit enhancement/monoline guarantor
7. | Clarification of roles for Sub-national bond and ISPO issuance process | CAMMIC, DMO, HMF |  |  | A process flow-chart to be released by SEC with steps for all categories of issuers
8. | Framework for prompt approval of short term bonds | SEC, HMF |  |  | Framework developed in conjunction with FMDQ, to be launched today
In progress
80% completed
In progress
10% completed
In progress
10% completed
In progress
30% completed
In progress
40% completed
Done
80% completed
Done
100% completed
95% completed
In progress

## Slide 6
DASHBOARD OF ISSUES RELATED TO F.I.R.S.
SN | Task/Issue | Assigned to | Status | Completion level | Expected Outcome
1. | Guidelines on tax treatment of REITs | SEC, FIRS |  |  | SEC/FIRS to finalize guidelines and rules to incentivize use of REITs
2. | Guidelines on tax treatment of sukuk | FIRS |  |  | FIRS to release guidelines granting sukuk same tax treatment as conventional bonds
3. | Tax treatment of companies with holding company structure | CAMMIC, FIRS |  |  | FIRS to issue guidelines that grant companies with HoldCo structure same tax benefits as banks with similar structure
4. | Tax deductibility of listing expenses | FIRS |  |  | Guidelines from FIRS allowing listing expenses to be tax deductible to encourage more listings
5. | Waiver on tax penalties and interest | FIRS |  |  | Currently being implemented by FIRS
6. | Minimum tax and excess dividend tax guidelines | FIRS, HMF, NASS |  |  | Pending amendment of CITA by NASS, FIRS treating this on a case by case basis. Minimum tax to be eliminated to boost competitiveness
7. | Insurance industry tax issues | FIRS, CAMMIC NAICOM |  |  | FIRS and NAICOM working together to address all tax disincentives inhibiting growth of insurance industry
8. | Stamp duty on savings and investment products | CAMMIC, HMF |  |  | Specific duty incentives for savings and investment products
9. | Inter-agency information sharing to boost tax compliance | HMF, all agencies |  |  | A unified portal for reporting to all agencies under the Ministry of Finance to boost tax compliance
10. | Improve tax compliance within the capital market | SEC, FIRS |  |  | Measures to ensure capital market participants comply with tax laws
In progress
80% completed
In progress
70% completed
Done
100% completed
In progress
60% completed
In progress
40% completed
In progress
40% completed
In progress
20% completed
20% completed
In progress
In progress
80% completed
In progress
70% completed
FIRS

## Slide 7
Next Steps…
3rd roundtable with HMF (26th Nov 2016)
Itemized initiatives for implementation in 2017
Continuous synergy in implementation process