## Slide 1
November, 2016
Presentation
to
Capital Market Committee Meeting
Lagos
Full Dematerialization Report as at date

## Slide 2
Introduction:
Schedule of Registrars |  | 
S/N | Registrars | No. Of Security
1 | Africa Prudential Registrars | 28
2 | Cardinalsonte Registrars | 26
3 | EDC Registrars | 6
4 | Mainstreet Registrar | 6
5 | Meristem Registrars | 22
6 | Veritas Registrars | 5
7 | GTL Registrars | 27
8 | Centurion Registrars | 4
9 | Unity Registrars | 4
10 | First Registrars | 27
11 | Pace Registrars | 9
12 | Flourmills Registrars | 2
13 | United Securities Ltd | 7
14 | Pac Registrars | 5
15 | Apel Registrars | 6
16 | Lighthouse Registrars | 1
17 | DataMax Registrars | 3
18 | Allcrown Registrars | 2
 |  | 190
The full dematerialization initiative commenced in July 2015 arising from SEC’s directive to all Registrar to work in concert with CSCS.
We had 190 securities managed by 18 Registrars

## Slide 3
Current Status
Due to the commitment of the parties to the initiative, we were able to overcome the challenges: Reconciliation were done between the Registrars and CSCS;
We have dematerialized 98.9%, translating to 187 securities successfully completed as at October 2016.
STOKVIS Nigeria Plc was delisted from the official list of the Nigerian Stock Exchange which reduced the total number of registers from 190 to 189.
The remaining 1.1% which represents two (2) securities are being reconciled for issued share capital discrepancies.
We are working with the affected two registrars to ensure 100% full dematerialization.
Authorized share capital
Issued Share Capital
Data mismatch
File categorization
Withdrawal of processed records
The Initial Challenges

## Slide 4
Registrars’ Performance On Full Demat As at Date
S/N | REGISTRAR | NO. OF REGISTER(S) | NO. TURNED IN | NO. UPLOADED | NO. READY TO BE UPLOADED | NO. REJECTED | % of successful Upload | REASON FOR REJECTION
1 | Africa Prudential Reg.Plc | 28 | 28 | 28 | - | - | 100% | 
2 | Cardinalstone Registrars | 26 | 26 | 26 | - | - | 100% | 
3 | EDC Registrars Ltd | 6 | 6 | 6 | - | - | 100.% | 
4 | Mainstreet Registrars Ltd | 6 | 6 | 6 | - | - | 100% | 
5 | Meristem Registrars Ltd | 22 | 22 | 22 | - | - | 100% | 
6 | Veritas Registrars Ltd | 5 | 5 | 5 | - | - | 100% | 
7 | GTL Registrars Ltd | 27 | 27 | 27 | - | - | 100% | 
8 | Centurion Registrars Ltd | 4 | 4 | 4 | - | - | 100% | 
9 | Unity Registrars Ltd | 4 | 4 | 4 | - | - | 100% | 
10 | First Registrars Limited | 27 | 27 | 27 | - | - | 100% | 
11 | PACE Registrars | 9 | 9 | 9 | - | - | 100% | 
12 | Flour Mills Registrars Ltd | 2 | 2 | 2 | - | - | 100% | 
13 | United Securities Ltd | 7 | 7 | 7 | - | - | 100% | 
14 | Pac Registrars Ltd | 4 | 4 | 3 | - | 1 | 75% | ISSUED SHARE CAP
15 | Apel Registrars Limited | 6 | 6 | 6 | - |  | 100% | 
16 | Lighthouse Securities | 1 | 1 | 1 | - | - | 100% | 
17 | Datamax Registrars Ltd | 3 | 3 | 2 | - | 1 | 66.7% | ISSUED SHARE CAP
18 | Allcrown Registrars Ltd | 2 | 2 | 2 | - | - | 100% | 
 | TOTAL | 189 |  | 187 |  |  |  | 
*Total Registers Successfully Uploaded = 187
*Percentage of successful upload = 98.9%

## Slide 5
Thank you