## CAMMIC Led Initiatives
MP Initiative: | Mainstream the 10 Year Capital Market Master Plan (CMMP) into National Economic Development Policy
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | CAMMIC Role
Promote ownership at the National level Engagements to facilitate Capital-Raising to fund National Economic Priorities | Prepare Position Paper | Position Paper | Apr 2016 | TA, CMPMT | Review and Adopt
| Arrange strategic engagements | Confirmed dates, meeting documents | 2016-05-01 | CMPMT, SEC DG | Agree dates
| Engage MoF | Ministerial Buy-in | Jun 2016 | CMPMT, CAMMIC, MoF | Lead Meeting
| Engage MoB&NP on co-opting the CMMP into exisiting Development Plan | Ministerial Buy-in | 2016-06-01 | CMPMT, CAMMICMoNB&P | Lead Meeting
| Engage MoT&I | Ministerial Buy-in | 2016-06-01 | CMPMT, CAMMIC, MoT&I | Lead Meeting
| Engage CBN | Buy-in | 2016-06-16 | CMPMT, CAMMIC, CBN | Lead Meeting
| Meet VP | VP's Buy-in | 2016-07-01 | CMPMT, CAMMIC, VP's Office | Lead Meeting
| Presentation at FEC | FEC Approval of CMMP as National Plan | 2016-08-01 | Ministers of B&NP and Finance, SEC | Attend FEC Presentation
| Follow-up commitments by relevant MDAs | Buy-in by relevant MDAs & stakeholders | Ongoing | CMPMT, TA, MDAs | Advisory
|  | Adoption of CMMP by FEC as part of National Economic agenda | 2016-12-01 | MDAs, others | None
MP Initiative: | Attracting More Listings
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | CAMMIC Role
Stakeholder engagement to promote new listings | Prepare for target engagements (Materials, logistics) | List of companies, Presentations, confirmed dates, other arrangments | 2016-05-01 | CMPMT | Review and Approval
| Engage TELCOs (MTN, Etisalat, Glo, Airtel,etc ) | MTN Feedback on lisiting commitment | 2016-07-01 | CMPMT, CAMMIC, MTN | Lead Engagements
| Engage NNPC/Minister of State for Petroleum | Listing commitment, structure & timetable | 2016-07-01 | CMPMT, CAMMIC NNPC, Minister | Lead Engagements
| Hold Industry based Round Table | Commencement of Listing process | 2016-10-01 | CMPMT, CAMMIC, target companies | Lead Roundtable
Engagement with MDAs to promote and incentivize listing | Prepare for target engagements (Position paper, logistics) | List of MDAs, presentations, dates, other arrangements | 2016-05-01 | CMPMT | Review and Approval
| Obtain updates from NSE on the listing agenda | Status of previous efforts | 2016-05-01 | CMPMT, SEC, NSE | None
| Prepare report on listing incentives (incorporate into position paper on mainstreaming) | Report/presentation on incentives | 2016-05-01 | CMPMT, SEC, TA | Review and Approval
| Engage FIRS/MoF on granting incentives | Listing Incentives from Gov't | 2016-11-01 | CMPMT, CAMMIC, FIRS, MoF | Lead Engagements
| Engage BPE | Identification of SOEs to be sold/ privatized SOEs with listing clauses | 2016-07-01 | CMPMT, SEC, BPE | Advisory
| Engage National Council on Privatization(NCP) | Commitment to encourage listing of Privatized Enterprises | 2016-07-01 | CMPMT, CAMMIC, NCP | Lead Engagements
| Engage Ministry of PW&H/NERC | Status of listing clauses for DISCOS & GENCOS | 2016-07-01 | CMPMT, CAMMIC, NERC, MoPW&H | Lead Engagements
| Engage Ministry of Comm. Tech./NCC | Commitment to TELECOMs listing | 2016-07-01 | CMPMT, CAMMIC, NCC, MoCT | Lead Engagements
| Engage VP | Additional incentives to listed companies | 2016-07-01 | CMPMT, CAMMIC, Presidency | Lead Engagements
MP Initiative: | Establish a Unified Licensing Model across the Money and Capital Markets
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | CAMMIC Role
Develop and implement Framework for Unified Licensing | Constitute Working Group (SEC, CBN & market representatives) | WG | 2016-05-01 | CMPMT, SEC, CBN, selected CMO representatives | Advisory
| Develop Terms of Reference for working group | WG ToR | 2016-05-01 | CMPMT, TA, CAMMIC | Review
| Develop Framework | Unified Licensing Framework | Jul 2016 | Working Group, CAMMIC, CMPMT | Review and Approval
| Implement Framework | New Licensing regime | 2017-02-01 | Working Group, SEC, CBN, CAMMIC, CMPMT | Guidance, Advocacy, Monitoring
MP Initiative: | Establish a National Savings Strategy
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | CAMMIC Role
Facilitate the establishment of a National Savings Strategy (NSS) | Constitute a Technical Committee (TC) | TC | 2016-05-01 | SEC, CMPMT, CAMMIC | Advisory
| Carry out research and develop position paper | Position Paper on NSS | Jun-16 | TC, CMPMT | Review and Approve
| Present paper to MoF and MoB&NP | Ownership of NSS by MoF | 2016-08-16 | CAMMIC, CMPMT, TC, MoF, MoB&NP | Lead presentation
| Constitute a National Working Group (NWG) | NWG inauguration | 2016-09-01 | MoF | Advocacy, Advisory
| Develop the NSS | NSS Framework | 2016-01-17 | Working Group | Advocacy, Advisory
| Launch of the NSS by the Presidency | NSS Launch at FEC | 2017-03-01 | MoF, Presidency | Attendance
| Implementation of the NSS | Monitoring and Evaluation reports | Ongoing | SEC, MoF, CAMMIC | Monitoring

## SEC Led Initiatives
MP Initiative: | Building the SEC's Human Capital Capacity
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Undertake HCM Gap Analysis | Set-up of working group (WG) | WG | 2016-04-01 | CMPMT, DG | Information
| Communicate Master Plan expectations to Working Group for 2016 | Memo to WG on expectations for 2016 | 2016-04-01 | CMPMT, REP, HR | Information
| Secure approval for project plan | Approval to embark on Gap Analysis | 2016-05-01 | HR, DG, WG | Advisory
| Produce and submit report | Report on Gap analysis | 2016-06-16 | WG, HR | Advisory
| Implementation | Improved human capital capacity | Ongoing | Management | Advisory
| Monitor Implementation | Periodic Status Reports | Ongoing | CMPMT, REP, HR | Advisory
Develop and implement Competency Management Framework Improve Performance Management and Succession Planning | Engage WG (Same as above) | Status on Competency Framework in the Commission | 2016-04-01 | CMPMT, REP, HR | Information
| Working Group develops project plan | Project Plan | 2016-05-01 | WG, HR | Advisory
| Secure approval for project plan | Approval of project | 2016-05-01 | WG, HR, DG | Information
| Engage consultants | Consultancy services | 2016-06-01 | WG, HR, P&SS, DG | Advisory
| Develop framework and performance management system | Competency Management Framework, Performance Mgt. System | 2016-07-01 | WG, HR, Consultant | Advisory
| Implement framework and system | Monitoring reports | Ongoing | WG, HR, Consultant, DG | Advisory
Training and Career Development | Develop 5 Year Training Master Plan | Training Master Plan | Nov-16 | WG, HR, Consultant | Advisory
| Breakdown training Master Plan into yearly plans | 2017 Training Plan | 2016-11-01 | HR | Advisory
MP Initiative: | Developing the Non-interest Capital Market Products (NICMP) Sector
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Expand NICMP offerings in the market Improve access to Liquidity and expand liquidity management instruments | Continuous engagement with CBN on Sukuk guidelines | Issued guidelines on liquidity status for Sukuk | May-16 | TC, CBN | Advisory
| Continuous engagement with DMO on Sovereign Sukuk | Sovereign Sukuk Issuance | 2017 | TC, DMO | Advisory
| Engage State Gov'ts on Sukuks, other NICMPs | Sub-sovereign Sukuk issuance | 2017 | TC, State Gov'ts | Advisory
| Continuous engagement with relevant stakeholders | Enlightenment and expanded NICMP offerings | Ongoing | TC, Others | Advisory
| Engage CBN, others on Liquidity Mgt. instruments | New Liquidity Instruments for Non-interest institutions | 2016-10-01 | TC, CBN | Advisory
MP Initiative: | Build Required Industry Wide Technology Infrastructure
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Undertake assessment of ICT needs | Constitute Technical Committee (TC)/Engage Consultant | TC Inauguration | 2016-04-01 | CMPMT, DGO | Advisory
| Prepare terms of reference (ToR) for TC | ToR | 2016-05-16 | CMPMT, TA | Advisory
| Develop raad map | Market-wide ICT Roadmap | 2016-09-16 | IT, TA, External consultant | Advisory
| Engage USAID, DFID, World Bank | Donor funding commitment | 2016-11-01 | CMPMT, DG Office, TA | Advisory
| Roadmap implementation | Implement roadmap | 2017 | SEC, CMC | Advisory
| Monitoring and Evaluation | Monitoring reports | Ongoing | CMPMT,IT, TA, Consultants | Advisory
Define Minimum Technology Standard for the Capital Market Implement real-time market surveillance system
| Roundtable with stakeholders to define standards | Defined standard for the market & the Commission | 2016-09-01 | SEC, SROs, Trade group | Advisory
| Engage relevant experts | Contract | 2017 | SEC, TC, relevant experts, IT Dept, SROs | Advisory
| Implement and monitor compliance with the standard | New standards take-off, monitoring and compliance reports | 2017 | SEC, SROs, Trade group | Advisory
Enhance technology and automate processes within SEC | Assign responsibility to ICTMIA | ICTMIA | 2016-05-01 | IT Dept, Project Team, relevant dept, experts | Advisory
| Scope Project & develop project plan | Project implementations plan | 2016-07-01 | Project Team | Advisory
| Engage relevant experts | Contract | Nov-16 | IT Dept, Project Team, relevant dept, experts | Advisory
| Automate relevant processes | E-registration, E-filing, etc | 2017 | IT Dept, Project Team, relevant dept, experts | Advisory
Promote adoption of shared services across the market | Technical Committee (same as above) to advise on services to be shared | Reporton shared services | 2016-05-16 | Market Development, IT Department, Technical Committee, SROs, CMOs | Advisory
| Engage stakeholders | Buy-in of stakeholders | 2016-06-01 | Market Development, IT Department, Technical Committee, SROs, CMOs | Advisory
| Standardize shared services framework | Framework for shared services | 2016-10-01 | Market Development, IT Department, Technical Committee, SROs, CMOs | Advisory
| Project take-off | Operationalised shared Services | 2017 | Market Development, IT Department, Technical Committee, SROs, CMOs | Advisory
MP Initiative: | Capital Market Literacy Schools and Mass Media initiative
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Introduce a Capital Market Literacy week | Set-up of working group (WG) | Working Group | 2016-03-01 | CMPMT | None
| Identify and select appropriate activities | List of activities segregated according to levels i.e Primary, secondary and tertiary schools | 2016-05-16 | CMPMT, MDD, ERD | Review and Advice
| Expose selected activities to relevant SROs & Trade Groups | Buy-in of SROs & Trade Groups | 2016-06-01 | CMPMT, MDD, ERD, SROs | Review and Advice
| Prepare Papers for presentations | Copies of final papers to present | 2016-08-01 | CMPMT, MDD, ERD, Trade Groups, SROs | Review and Advice
| Prepare time-table of activities | Copy of comprehensive timetable of activities | 2016-08-01 | MDD, ERD, CMPMT, TA, DG | Review and Advice
| Roll-out of Literacy Week. | Activities in schools in all regions of Nigeria | 2016-10-01 | CMPMT, TA, SROs, Trade Groups, MDD, ERD | Participate
Reactivate TV and radio literacy programmes (e.g. You and the Capital Market) | Identify & select areas of focus for the programs | Comprehensive strategy with justification for all areas of focus | 2016-05-01 | MDD, ERD, TA | Advisory
| Identify and select appropriate TV & Radio stations | List of selected TV & Radio Stations with justification and cost implication | 2016-05-01 | MDD, ERD, CMPMT, DG | Review and Advice
| Engage TV & Radio Stations (meetings & agreements) | Letters of Engagement | 2016-06-01 | MDD, ERD, DG | Advisory
| Activate internal monitoring mechanism for feedback | M&E Reports | 2016-06-01 | MDD, CMPMT,ERD, ETC. | Review and Advice
Target public awareness campaign through townhall meetings, road shows and advertisements | Prepare Proposal | Proposal containing focus areas, programmes, timelines, cost implication, locations, etc | 2016-04-01 | MDD, ERD, CMPMT, TA, DG | Review and Advice
| Identify & select relevant print & electronic media organizations | List of selected organizations, justification and cost implication | 2016-05-01 | ERD, DG | Review and Advice
| Place advertorials in selected print & electronic media | Approved messages based on focus areas | On going | ERD, MDD, CMPMT | Review and Advice
| Activate internal monitoring mechanism for feedback | M&E Reports | On going | CMPMT,ERD, MDD ETC. | Review and Advice
Introduce capital market studies into school curriculum at all levels | Obtain update from MDD on progress made so far | Status Reports | 2016-04-01 | MDD, CMPMT
| Arrange Strategic engagements with NERDC, FME, NUC | Buy-in of relevant stakeholders | Apr 2016 - Jun 2016 | MDD, WG, relevant stakeholders | Review and Advice
| Finalize School curriculums and begin implementation | Implementation of the various classes of school curriculums | 2016-12-01 | MDD, WG, relevant stakeholders | Review and Advice
MP Initiative: | Transaction Cost Reduction
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Implementation of Transaction Cost Reduction | Continuous engagements between the TC and relevant stakeholders | Agreed Cost Structure | 2016-12-01 | SEC, SROs, CMOs | Review and Advice
| Implement New Cost Structure | Compliance reports | 2017 | SEC, SROs, CMOs | Advisory
MP Initiative: | Building an Enabling Framework for the Derivatives Market
Sub-Projects | Tasks | Deliverables | Timeline | Responsibility | TA Role
Prioritize capacity building on Derivatives | Identify world class training programmes on derivatives | Training Programmes on Derivatives | 2016-10-01 | HR, CMPMT | Advisory
| Relevant courses on derivatives delivered to selected number of staff of the Commission | Increased staff capacity on Derivatives | 2017 | HR, Training oufit | Information
| Placement/secondment of relevant staff to jurisdictions with vibrant derivatives markets | Increased staff capacity on Derivatives | 2017 | HR, stakeholders | Information

## CAMMIC Calendar
Activity Calendar for CAMMIC
S/N | Initiatives/Activities | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
1 | Mainstream the 10 Year CMMP into National Economic Development Policy
A | Review and Adopt Position Paper | 2016-03-01: Week 2
B | Engagement with Minister of Finance (MoF) | 2016-05-01: Week 1
C | Engagement with Minister of Budget and National Planning (MoB&NP) | 2016-05-01: Week 1
D | Engagement with Minster of Trade and Investment | 2016-05-01: Week 1
E | Engagement with VP (led by MoF & MoB&NP) | 2016-06-01: Week 4 Or Week 1
2 | Attract more Listings (TELCOS, GENCOS, DISCOS, O&G, SMEs, etc)
A | Review list of target companies/SOEs to engage and approve content | 2016-03-01: Week 2
B | Engagement with MTN | 2016-06-01: Week 1
C | Engagement with NNPC/Minister of State for Petroleum | 2016-06-01: Week 1
D | Hold Industry based roundtable | 2016-10-01: Week 3
E | Review Paper on Proposed incentives for listing | 2016-03-01: Week 4
F | Engagement with MoF & FIRS on Incentives | 2016-05-01: Week 1; 2016-09-01: Week 3
G | Engagement with National Council on Privatization(NCP) | 2016-06-01: Week 1
H | Engagement with Minister of PW&H/NERC | 2016-07-01: Week 2
I | Engagement with Minister of Comm. Tech./NCC | 2016-07-01: Week 2
J | Engagement with VP (led by MoF & MoB&NP) | 2016-06-01: Week 4 Or Week 1
3 | Establish a Unified Licensing Model across the Money and Capital Markets
A | Review and adopt Framework for Unified Licensing | 2016-07-01: Week 4
B | Periodic review of implementation activities | 2016-08-01: Week 4; 2016-11-01: Week 4
4 | Establish and implement a National Savings Strategy (NSS)
A | Review and adopt concept paper on National Savings Strategy | 2016-04-01: Week 2
B | Engagement with MoF on NSS | 2016-05-01: Week 1
C | Engagement with MoB&NP on NSS | 2016-05-01: Week 1
Key
Activity Dates
Engagements with MoF happening on same day
Engagements with MoB&NP happening on same day
Engagements with VP happening on same day

## Sheet1
MP Initiative: | Building the SEC's Human Capital Capacity
Sub-Projects | Recommendation | DG's Comments
Undertake HCM Gap Analysis | Set up a HRM Reforms Working Group
Develop and implement Competency Management Framework Improve Performance Management and Succession Planning | Working Group to plan and implement projects
Training and Career Development | WG to take up assignment