## Slide 1: Technical Committee on National Savings Strategy
Preliminary Report at the Second CMC Meeting

## Slide 2: Membership
2
S/N | NAME | ORGANIZATION
1 | Michael Oyebola | Chairman
2 | Ore Sofekun | Investment One/President FMAN
3 | Shuaib Audu | Stanbic IBTC Capital Ltd.
4 | Bukar Kyari | CSCS Nigeria Plc.
5 | Funmi Ekundayo | STL Trustees/President ACT
6 | Dr. Hassan Hassan Suleiman | SEC
7 | Isi Patience Ayede | SEC (Secretary)
Notes: Content page, sub-section divide, used at start of sub section only

## Slide 3: Terms of Reference
3
MP Initiative: | Establish a National Savings Strategy |  | 
Sub-Projects | Tasks | Deliverables | Timeline
Facilitate the establishment of a National Savings Strategy (NSS) | Constitute a Technical Committee (TC) | TC | Jul-16
 | Carry out research and develop position paper | Position Paper on NSS | Aug-16
 | Present paper to MoF and MoB&NP | Ownership of NSS by MoF | Sep-16
 | Constitute a National Working Group (NWG) | NWG inauguration | Sep-16
 | Develop the NSS | NSS Framework | Jan-17
 | Launch of the NSS by the Presidency | NSS Launch at FEC | Mar-17
 | Implementation of the NSS | Monitoring and Evaluation reports | Ongoing
Notes: Content page, sub-section divide, used at start of sub section only

## Slide 4: Actions So Far
Technical committee established July 18, 2016;
Held Inaugural Meeting on August 3, 2016;
  Set strategy for development of a position paper;
  Set timeline for achieving a National Savings Strategy;
  Position paper will be presented to the SEC before presentation to MoF and MoB&NP;
  Formal launch of Position Paper/Working Document on World Savings Day – October 31, 2016

## Slide 5: Topics For Developing Position Paper
A review of the Nigerian Economy:
  Historical Perspective of the:
    GDP numbers
    Per capita income
    Investment & Capital Formation and as a % of GDP
    Savings as a % of GDP
    Identify Savings-Investment gap (if any)
  An analysis of the Nigerian Demographics (past, current, projected)
    Total Population
      By age groups
      By gender
      By worker groups
        Formal
        Informal

## Slide 6: Topics For Developing Position Paper
Savings and the economics behind it, including a review of:
  Voluntary, involuntary and forced savings
  Types of Savings
    Long Term Savings
    Medium Term Savings
    Long Term Savings
  The taxation of savings and its effects
  State of and quantum of domestic savings - formal and informal and identify gaps (if any)
    Bank savings – including Mortgage banks, Micro finance banks, etc
    Pensions savings
    Capital Market – stock broking accounts and values
    Collective Investment Schemes
    Insurance pools
    Cooperative societies
    Ajo/Esusu; Akawo; Adashe, etc

## Slide 7: Topics For Developing Position Paper
A review of the Nigerian Financial System:
  Its current Structure
  Current Legislation & Regulations
  The past, present and future state
    Participants
      Regulators and how they regulate
      Regulated and how they are regulated
  The role Financial Inclusion and Financial Education play and have played
    Banked
    Unbanked
    Financially excluded
  The role of payment systems

## Slide 8: Topics For Developing Position Paper
Case studies for countries with National Savings Strategies
  UK
  Malaysia
  Rwanda
  Ghana
  India
  Singapore

## Slide 9: Developing Position Paper
Do we need a National Savings Strategy?
Information and analysis of the above can help us answer this question and then lead us to coming up with a National Savings Strategy (or not), including:
    what the pillars of a successful National Savings Strategy are,
    the kind of products we need (there’s a committee of products),
    how to mobilize national savings; and
    the implementation of the National savings strategy.

## Slide 10: TImelines
STRATEGY | MODALITIES
Carryout research and deliver papers for review | To 16 August, 2016
Identify the pillars of a successful National Savings Strategy, the products to mobilize these savings, mode of mobilization and implementation of the strategy | Meet to discuss review research and there after harmonize and produce a Position Paper – from August 17, 2016 to mid-September
Presentation of position paper to SEC, then MoF & MoBNP | September, 2016 Target is to at least have the final position paper ready which can be used to develop the framework for launch on World Savings Day – 31 October 2016

## Slide 11: Thank you Comments?