## Slide 1: TECHNICAL COMMITTEE ON ATTRACTION OF NEW LISTINGS
UPDATE ON NEW LISTINGS INITIATIVES
for
CAPITAL MARKET COMMITTEE (CMC)

## Slide 2: OUTLINE
1
NEXT STEPS
4
UPDATE: ENGAGEMENTS WITH MDA’S
3
OUR MANDATE
5
CHALLENGES TO IMPLEMENTATION
2
UPDATE ON INITIATIVES

## Slide 3: OUR MANDATE
Mandate: To drive advocacy and other activities towards increasing the number of listed companies on our exchanges.
Broad Terms of Reference are:
Propose strategies to attract listings form target sectors
Undertake relevant advocacy
Undertake any other activity that may be relevant to the achievement of its mandate

## Slide 4: UPDATE ON INITIATIVES
TC Initiative: | Attracting More Listings |  |  | 
Initiatives | Tasks | Deliverables | Indicative Timeline | Status
(A) Engagement with Industry Groups to explore listing opportunities | Identify Industry groups to be sensitized | (i) Create list of prospective industry groups (ii) Create timelines for sensitization | 30-Aug-16 | Done
 | Preliminary meeting with each industry group | Get feedback on impediments to listings | 30-Nov-16 | Done
 | Follow up meeting with industry groups | Secure Listing buy-in | 15-Dec-16 | On-going
 | High-Value Issuers engagement (e.g. NNPC/ Minister of State for Petroleum) | Tentative listing commitment, structure & timetable | 15-Dec-16 | On-going
(B) Engagement with MDAs to promote and incentivize listing | Identify MDA's to be engaged | List of MDAs, presentations, timelines and dates. | 30-Aug-16 | Done
 | Prepare report on listing incentives. | Prepare report on incentives that will encourage listing | 30-Sep-16 | Done
 | Engage FIRS/MoF on granting incentives | Engage on tax incentives to encourage listing | 15-Dec-16 | On-going
 | Engage BPE | Identification of SOEs to be sold/ privatized SOEs with listing clauses | 1-Dec-16 | On-going
 | Engage Ministry of Finance | Engage with ministry of finance on the possibility of listing government assets in their portfolio. | 15-Dec-16 | On-going
 | Engage National Council on Privatization(NCP) | Commitment to encourage listing of Privatized Enterprises | 1-Dec-16 | Yet to be done
 | Engage Ministry of PW&H/NERC | Status of listing clauses for DISCOS & GENCOS | 9-Nov-16 | Done
 | Engage Ministry of Communications and Information Technology/NCC | Get Buy-In on encouraging listing of Telecoms | 1-Dec-16 | Done
(C) Engagement with capital market regulators | Engagement with SEC | (i) Engage SEC on rules impeding issuer listing (ii) Engage SEC on regulatory initiatives that would support listing based on feedback from Industry Groups | 15-Nov-16 | On-going
 | Engagement with SEC/NSE | Engage SEC/NSE to fast track listing by streamlining listing process | 15-Nov-16 | On-going

## Slide 5: UPDATE: ENGAGEMENTS WITH MDAs
AGENCY | KEY HIGHLIGHTS
AMCON Asset Management Company of Nigeria | AMCON recognizes the need to contribute to the development of the Nigerian capital market, through issuances of REITs; exiting equity holdings through the capital market; and participating in the securities lending market. A sub-committee was set up to work with AMCON to develop a viable framework for AMCON to access the capital market.
BPE Bureau of Public Enterprises | The BPE explained the challenges it faces in listing SOEs in the capital market. A sub-committee was set up, comprising members of the TC and the BPE. The TOR of the sub-committee and its implementation framework has been developed. The intent of the sub-committee is to examine SOEs and privatized companies, which can be listed in the capital market and also develop a roadmap to bring these companies to the market in the least time possible.
BPP Bureau of Public Enterprises | A previous engagement was held with the BPP where it was decided that the TC should develop a proposal on preferential procurement policy for listed companies. The proposal was developed and presented to the BPP, and they showed willingness to work with the TC in implementing the proposal.
MoFI Ministry of Finance Incorporated | MoFI is the custodian of assets owned by the Government. MoFI provided the TC with an updated list of all assets owned by the Government for further engagement with the ministry of finance.

## Slide 6: NEXT STEPS
BPE – TC’s sub-committee on BPE, to work on resolving challenges facing the listing of SOEs and privatized companies in the market; identify list of SOEs that can be listed; and develop viable framework to bring these SOEs to the market in the shortest possible time.
AMCON – TC’s sub-committee on AMCON to resolve challenges facing AMCON in issuing REITs; exiting equity holdings through the capital market; and participating in the securities lending market.
BPP – Further engage the BPP on how the incentive on preferential procurement policy for listed companies can be incorporated into BPP’s guidelines.
Follow up – Follow-up on preliminary meetings with IPMAN, REDAN, MAN and Joint Partnership with NNPC.
Continue engagements with other regulators and industry groups such as MOFI and African Private Equity and Venture Capital Association (AVCA).
Make input into report of NSE/SEC Committee on streamlining of listing process as this has a considerable impact on the TC’s mandate.
Hold a listing and issuance conference involving all stakeholders in the market.

## Slide 7
CHALLENGES TO IMPLEMENTATION
  Budget for listings and issuance round table conference: The TC would require support from regulators and CMOs for a successful conference.