## Slide 1
CAPITAL MARKET COMMITTEE (CMC)
TECHNICAL COMMITTEE ON ATTRACTION OF NEW LISTINGS
UPDATE ON NEW LISTINGS INITIATIVES
PRESENTATION TO
CAPITAL MARKET COMMITTEE (CMC)
9th May 2017
by
HARUNA-JALO WAZIRI
CHAIRMAN

## Slide 2
Our Mandate
Update on Initiatives
Highlight of key comments from Preliminary Meetings
Outcome of Preliminary Meetings
Next Steps
OUTLINE

## Slide 3
OUR MANDATE
Mandate: To drive advocacy and other activities towards increasing the number of listed companies on our exchanges.
Broad Terms of Reference are:
Propose strategies to attract listings form target sectors
Undertake relevant advocacy
Undertake any other activity that may be relevant to the achievement of its mandate

## Slide 4
TC Initiative: | Attracting More Listings |  |  | 
Initiatives | Tasks | Deliverables | Indicative Timeline | Status
(A) Engagement with Industry Groups to explore listing opportunities | Identify Industry groups to be sensitized | (i) Create list of prospective industry groups (ii) Create timelines for sensitization | 30-Aug-16 | Done
 | Preliminary meeting with each industry group | Get feedback on impediments to listings | 30-Nov-16 | Done
 | Follow up meeting with industry groups | Secure Listing buy-in | 15-Dec-16 | On-going
 | High-Value Issuers engagement (e.g. NNPC/ Minister of State for Petroleum) | Tentative listing commitment, structure & timetable | 15-Dec-16 | On-going
(B) Engagement with MDAs to promote and incentivize listing | Identify MDA's to be engaged | List of MDAs, presentations, timelines and dates. | 30-Aug-16 | Done
 | Prepare report on listing incentives. | Prepare report on incentives that will encourage listing | 30-Sep-16 | Done
 | Engage FIRS/MoF on granting incentives | Engage on tax incentives to encourage listing | 15-Dec-16 | On-going
 | Engage BPE | Identification of SOEs to be sold/ privatized SOEs with listing clauses | 1-Dec-16 | Yet to be done
 | Engage Ministry of Finance | Engage with ministry of finance on the possibility of listing government assets in their portfolio. | 15-Dec-16 | Yet to be done
 | Engage National Council on Privatization(NCP) | Commitment to encourage listing of Privatized Enterprises | 1-Dec-16 | Yet to be done
 | Engage Ministry of PW&H/NERC | Status of listing clauses for DISCOS & GENCOS | 9-Nov-16 | Done
 | Engage Ministry of Communications and Information Technology/NCC | Get Buy-In on encouraging listing of Telecoms | 1-Dec-16 | Done
(C) Engagement with capital market regulators | Engagement with SEC | (i) Engage SEC on rules impeding issuer listing (ii) Engage SEC on regulatory initiatives that would support listing based on feedback from Industry Groups | 15-Nov-16 | On-going
 | Engagement with SEC/NSE | Engage SEC/NSE to fast track listing by streamlining listing process | 15-Nov-16 | On-going
UPDATE ON INITIATIVES

## Slide 5
NERC Nigerian Electricity Regulatory Commission 9th November, 2016 |  | The regulator is open to ideas that would fund the liquidity shortfall in the industry. Suggested options included; sale of govt. 40% shareholding and a bond issuance guaranteed by FGN. TC to meet with DISCOs and GENCOs to understand the issues facing the sector from their perspective. Prepare formal proposal on how the sector can fund its liquidity crisis.
BPP Bureau of Public Procurement 10th November, 2016 |  | Proposed strategy was to Incentivize companies to list by giving preference to public listed companies during procurement bids. Constrained by its ACT which already stipulates requirements for bid qualification. BPP is open to innovative suggestions from the committee on how to include incentives in its guidelines.
REDAN Real Estate Developers Association 10th November, 2016 |  | Acknowledges that accessing the capital market for long term funds is the only way to solve the housing deficit in the country. Lack of information on the capital market and how to convert from private to public. Lack of information on how to access the market to fund projects. Also lack information on listing requirements and processes.
IPMAN Independent Petroleum Marketers Association 9th November, 2016 |  | Association has about 10,000 members who own over 30,000 retail outlets across the country. Acknowledges the need for members to build sustainable companies. Lack information on the benefits of listing and listing process. Fear of dilution of shareholding and losing control of company to outsiders if listed.
Highlights of key comments from preliminary meetings

## Slide 6
NCC Nigerian Communication Commission 9th November, 2016 |  | Proposed strategy was to incentivize companies to list by granting licensing fee rebate to listed companies and providing in its guidelines listing as a condition for license renewal. Constrained by its ACT which already stipulates requirements for license issuance and renewal.
FAAN Federal Airports Authority of Nigeria 29th November, 2016 |  | Acknowledges that the capital market was viable alternative source of funding /refinancing especially to local airlines which were highly leveraged. However, given recent developments where AMCON has taken over most of the airlines, the TC would rather engage AMCON on how it can exit the industry and its other portfolios via the capital market.
MAN Manufacturers Association of Nigeria 22nd November, 2016 |  | Major impediments to listings were; Current economic condition Low level of awareness of the capital market and the benefits of listing High level of foreign owned businesses and entrepreneurs fear of losing control of their business
NNPC Nigerian National Petroleum Corporation 6th December, 2016 |  | Acknowledges the need for its companies to be recapitalized to make them profitable and competitive via the capital market. NNPC has a 3-year timeline during which its subsidiaries would be restructured to get them fit for the capital market Proposed joint partnership with the TC to provide guidance and facilitate the process of listing NNPC and its companies on our Exchanges.
Highlights of key comments from preliminary meetings

## Slide 7
Outcome of preliminary meetings
ACTIVITY |  | STATUS
TC to prepare value propositions for the Telecoms Sector. |  | Recommendations to be presented to NCC
TC to recommend to BPP how listing initiatives can be incorporated into their guidelines. |  | Recommendations have been prepared, awaiting presentation to BPP
Obtain from CBN loan exposures of Oil and Gas marketers. |  | Awaiting response from CBN
Engage AMCON on how to exit its portfolios via the capital market as most airlines have been taken over. |  | Meeting with AMCON is being scheduled.
Formed joint partnership with NNPC to facilitate the listing of its subsidiaries. |  | Held one meeting with NNPC Capital on 8th Dec. 2016. Awaiting further directives from NNPC.
Review and make input into report of SEC/NSE committee on streamlining listing process. |  | Awaiting report of the Committee.
Prepare concept paper for listing and issuance conference. |  | Done. Request for sponsorship to be sent out ASAP

## Slide 8
Present to BPP recommendations on how incentives for listing can be incorporated into their guidelines.
Follow up on preliminary meetings with IPMAN , REDAN, MAN and Joint Partnership with NNPC.
Sensitize members of Industry Groups on benefits of listings.
Continue engagements with other regulators and industry groups such as AMCON, BPE, MOFI and African Private Equity and venture Capital Association.
Make input into report of NSE/SEC Committee on streamlining of listing process as this has a huge impact on our mandate.
Prepare report on incentives that will encourage listing.
Hold a listing and issuance conference involving all stakeholders.
Next Steps

## Slide 9
  Budget for listings and issuance round table conference: The TC would require support from regulators and CMOs for a successful conference.
Challenge

## Slide 10
THANK YOU
Questions & Answers