## Slide 1
2018 3RD CAPITAL MARKET COMMITTEE MEETING Wednesday, 14th November, 2018
PRESENTATION OF THE COMMODITIES TRADING ECOSYSTEM IMPLEMENTATION COMMITEE

## Slide 2
INTRODUCTION
SEC has upgraded its commodities exchange unit to a Division and currently strengthening its capacity.
It has reviewed the registration requirements for spot commodity trading and currently reviewing regulations generals, for spot commodity trading by the exchanges.
The Committee has arranged a meeting with the Institute of Public Analysts of Nigeria (IPAN), SGS Inspection Services and Standards Organization of Nigeria on the 22nd of November 2018 on issues of grading and standardization of agricultural commodities that are currently traded and likely to be traded on the exchanges.
The Committee and some of its members have engaged with some key stakeholders.
The various sub-committees on education, conference and mapping of warehouses have made progress on their assignment.
As part of the effort to de-risk the agricultural sector and improve its attraction to investors, the Committee is propose a small industry committee to include BOA and CBN to develop an agric based exchange tradable instrument / product.

## Slide 3
COMMODITIES TRADING ECOSYSTEM IMPLEMENTATION DASHBOARD |  |  | 
S/N | RECOMMENDATION | TIME LINE | RESPONSIBILITY
1 | Engagement with critical stakeholders (Vice President, Federal Ministry of Finance, Federal Ministry of National Planning, Federal Ministry of Agriculture and Rural Development, Federal Ministry of Industry, Trade and Investment, Central Bank of Nigeria, Standard Organization of Nigeria, Nigerian Sovereign Investment Authority) | Q4 2018-Q1 2019 | SEC, CAMMIC, Committee
2 | Education and Enlightenment Roadmap Report | Q4 2018 | Committee
3 | International Stakeholder Conference (Proposal to be ready by January 2019) | Q3 2019-Q4 2019 | Committee ,SEC
4 | Mapping of Warehouses | Q1 2019 | NCX, AFEX
5 | Capacity building for Investment and Securities Tribunal | Q1 2019 | SEC
6 | Rules for spot commodity market and other related rules | Q1 2019 | SEC
7 | Rules on collateral management | Q2 2019 | SEC
8 | Development of certification system for collateral managers | Q2 2019 | SEC, Committee

## Slide 4
9 | Workshop for collateral management companies | Q1/Q2 2019 | SEC
10 | Engagement with logistic companies | Q4 2018-Q1 2019 | NCX, AFEX, SEC
11 | Commodity exchanges to provide price information through collaboration with Federal Ministry of Agriculture and Rural Development | Q3 2019 | NCX, AFEX, FMARD, SEC
12 | Organising farmers into cooperatives (pilot) | Q4 2019 | NIRSAL, AFEX, FMARD, NCX, SEC
13 | Engagement with Governors Forum for delegation of land matters to relevant agencies | Q3 2019 | CAMMIC, SEC
14 | Work with Bank of Agriculture to develop agric based instruments that will be attractive to investors (sub-committee to be set up) | Q4 2018 | SEC
15 | Introduce risk-based capital for non-spot commodities market operators | Q1 2019 | SEC
16 | Engage with SON to develop efficient grading and standardization system for agriculture and solid minerals | Q2 2019 | SEC, Committee

## Slide 5: EDUCATION AND ENLIGHTENMENT ROADMAP

## Slide 6
INTERNATIONAL CONFERENCE ON COMMODITY EXCHANGE
Theme: Commodity Exchange: Key to diversifying Nigeria’s economy.
Structure of Conference:
No of Days – 2 – 3 days
Proposed Discussion Points:
Enabling Environment for a functioning commodity trading ecosystem
Geo-cooperatives: organizing farmers the smart way
Transforming existing infrastructure to meet commodity exchange demands
The African Experience – Lessons learned from Commodity Exchanges in Africa
Quality Control: GAP, Standardization and supporting regulation
The role of Government vs. Private Investors
Nigeria’s key commodities and global position/potential
Warehouse Receipting: Lessons learned from Ethiopia Commodity
Exchange
Commodity exchanges and Derivatives market
Developmental Challenges on commodity exchange in Africa
Innovative Mechanism in Global commodity exchanges
What will a functioning commodity exchange ecosystem bring to Nigeria’s economy?
What are the major trends and developments in commodity exchanges around the World
Cryptocurrencies, Blockchain Technologies in the commodities exchange ecosystem.

## Slide 7
Next Steps & Conclusions…