## Slide 1: 2019 1st CAPITAL MARKET COMMITTEE MEETING Thursday, 21st March, 2019
ROADMAP ON FUND MANAGEMENT

## Slide 2: CIS 5 Year Strategic Master Plan Road Map 2013 – 2018: Status Report
CIS Vision
Vision of Fund Managers Association of Nigeria (FMAN): Develop a multi-trillion naira collective investment scheme industry in Nigeria by 2018
23 Core Initiatives/Action Plan
15 point Action Plan: SEC implementation;
4 point Action Plan: FMAN implementation;
4 point Action Plan:
SEC/FMAN joint implementation
Status Report
70 % level of Completion/Implementation
SEC Action Plans: 11 APs implemented; 4 outstanding/WIP;
FMAN Action Plans: Ongoing/Work in Progress;
SEC/FMAN Action: Ongoing/Work in Progress

## Slide 3: CIS 5 Year Strategic Master Plan Road Map
S/N | Road Map Proposals/Issues raised | PREVIOUS POSITION | CURRENT POSITION | RESPONSIBLE PARTY | STATUS
1. | Distinction between Issuer and Fund Manager | S.152 defines Issuer as ‘Person performing duties of a Manager ……… | Proposal was rejected by SEC. ISA already provides position for ‘Promoter’ who is not same as Issuer but can sponsor an Issue | SEC | Resolved
2. | Fund Set Up/IPO | 6 – 18 months from filing to approval of allotment as a result of duplication of review process | Reduced to 14 days for Open ended Funds and 15 days for Closed Ended Funds. Rules review have been made, exposed and passed | SEC | Implemented
3. | REITS: Enhancement of existing Rules | REITS are part of CIS Rules. Road Map proposed re categorization, Resolution of Tax reliefs | Comprehensive review of Rules on REITs and structure were done in collaboration with StanbicIBTC. Rules had been exposed. Awaiting FIRS on Tax implementation | SEC | Implemented
4. | Redemption of Units | Inconsistencies btw S166 of ISA and nature of a Closed Ended Fund under S.171(1)(e) | SS 166 and 171(1)(e) were reviewed to particularly refer to Open Ended Funds and Closed ended Funds respectively. Amendment sent ISA review Committee | SEC | Addressed
5. | Segregation of Labilities under Umbrella Fund | No current statutory provision giving requiring segregation of Sub Funds liabilities | Rules reviewed to make provision for ring fencing assets and liabilities of each sub Fund of an Umbrella Fund | SEC | Implemented
6. | Draft Rule F3: Private Placement by public Coys and CIS | CIS Funds categorized under same Rule provision on Private Placement by Public Companies | CIS removed from that heading and reflected in current nules | SEC | Resolved

## Slide 4: CIS 5 Year Strategic Master Plan Road Map 2013 – 2018: Status Report
SN | Road Map Proposals/Issues to be addressed | PREVIOUS POSITION | CURRENT POSITION | RESPONSIBLE PARTY | STATUS
7 | Review Custodian Rule 456(f) | Rule 456(f) provides that Custodian be independent of Fund Manager and not be affiliated to either of the parties | Rule has been reviewed/amended to state that Custodian be independent of the Fund Manager ONLY | SEC | Resolved
8 | Fund Managers ’Fixed Proprietary Exposure to their Schemes | At time CIS Road Map was initiated, Issuer/FM was required to hold 10% holdings in the Fund | Rules reviewed to reduce a Fund Manager’s mandatory Holdings from 10% to 5% on initials units on Offer for the life of the Scheme | SEC | Resolved
9 | Review Table of Contents and other Errors in Consolidated Rule: Fund Categorization; Investment Committee membership | At time CIS Road Map was initiated. Errors in numbering of Rules and omission in Consolidated Rules were present; | Numbering errors have been reviewed and corrected; Number of independent members on an Investment Committee has been harmonized; Rules reviewed further to make provisions for different Fund Categories viz: Equity Funds, Fixed Income Funds, Ethical Funds etc. | SEC | Resolved
10 | Investor awareness | Very low level of investor participation | Technical Committee on Financial literacy (FL) has been set up and have commenced work on programs for FL | SEC/ FMAN | Ongoing
11 | Pricing | A Universal pricing nature for the different CIS Funds | Rule review done providing for different frequencies for daily computation of bid prices of Open Ended Funds | SEC | Resolved

## Slide 5: CIS 5 Year Strategic Master Plan Road Map 2013 – 2018: Status Report
 | Road Map Proposals/ SEC: Issues to be addressed | PREVIOUS POSITION | CURRENT POSITION | RESPONSIBLE PARTY | STATUS
12 | Governance | Fund Manager appoints independent members of the Investment Committee | Requirement for independent members of the Board of Trustees who will be responsible for appointment of Independent members of the Investment Committee and set their remuneration to ensure continued independence. This proposal was rejected by SEC. Trustees and independent members of the Investment Committee are already statutorily required to be independent of the fund Manager | SEC | Addressed
13 | Marketing Channel | Fund Manager are essentially sole channels for distribution of CIS products | FMAN worked in collaboration with CSCS, NSE and ASHON to successfully launch the Mutual Fund Trading Platform on the Nigerian Stock Exchange which now provides an alternative subscription channel for investors thereby enhancing financial inclusion | FMAN | Implemented
14 | Review/ Streamline Offer Process for CIS Funds | Requirement for Financial Forecast presentation in Offer Document High number of Offer parties, attendant cost to the Offer | Requirement for Financial forecast have been done away with as part of Offer document disclosure Offer Process for CIS Schemes reviewed providing for relevant parties and reduction of Offer Cost | SEC | Implemented
15 | Standardization of CIS Offer Documents | Diversity of Offer Documents preparation with respect to Trust Deeds, Custodial agreements etc | Standardization of key CIS Offer documents to a standardized template for respective document that can be adopted for use by the Market | SEC/ FMAN | Implemented

## Slide 6
Outstanding Issues/Work in Progress |  |  |  |  | 
SN | ROADMAP PROPOSALS/ SEC: ISSUES TO BE ADDRESSED | CURRENT POSITION | ACTION PLAN/ACTION BEING TAKEN | RESPONSIBLE PARTY | STATUS
1 | Tax Treatment of CIS Funds | CIS Funds being subject to Companies Income taxation, rather than treat as a ‘Pass through’ where tax is applied to dividend received by UH | CAMMIC subcommittee has been liaising with FIRS and Ministry of Finance on this | SEC | Ongoing
2 | Performance Evaluation | Non standardized performance evaluation that would allow for proper assessment and comparison of performance of Fund Managers | Planned adoption/implementation of the Global Investment Performance Standards. SEC will be meeting with FMAN to finalize position for implementation this year across sector | SEC/ FMAN | Ongoing
3 | Fees and Commission | Threshold limit of 5% Total Expense Ratio (TER) as provided by Rules. | TER to be reviewed downwards with greater scaling of Fund from increased investor subscription. | SEC/ FMAN | Ongoing
4 | Risk Based Supervision of Funds | Essentially a Compliance/Rules based approach. | Hybrid of Compliance/Risk Based Supervision approach since the segregated structure of the CIS ensures good measure of risk mitigation | SEC | To commence this year